## Project Plan
ROBOT BUILD PROJECT PLAN
Rounded-square robot • Raspberry Pi Pico W • colour face • four wheels underneath • optional tracks later
Project goal | Build a small rounded-square robot with a colour display for animated eyes, four powered wheels, a servo-operated camera mount, an obstacle sensor and phone-app control over Wi-Fi. Start with a wheeled prototype; add tracks and live camera video only after the basics work.
Planning budget (AUD) | See Parts & Costs tab; estimates only, verify current pricing and compatibility before buying.
ID | Stage / task | Instructions / deliverable | Dependency | Estimate | Status
P01 | Confirm design dimensions | Measure the display, Pico board, motors, wheel diameter, battery and camera mount. Draw the internal layout and wheel openings. Do not finalise the shell before measuring real parts. | None | 2–4 hours | Not started
P02 | Confirm compatible electronics | Choose motors and check their stall current against the motor-driver ratings. Confirm display interface/library, servo supply, battery voltage and regulated logic supply. | P01 | 2–3 hours | Not started
P03 | Order essential parts | Use the Parts & Costs tab. Buy only after checking seller stock, delivery, connectors and voltage/current specs. | P02 | 1 hour | Not started
P04 | Set up development computer | Install Thonny. Download the correct MicroPython UF2 for Pico W. Connect using a USB data cable; hold BOOTSEL while plugging in, then copy the UF2 file if needed. | P03 | 1–2 hours | Not started
P05 | First Pico test | In Thonny, select MicroPython for Pico. Run print('Hello robot'). Save a simple program to the Pico as main.py and confirm it runs after power cycling. | P04 | 1–2 hours | Not started
P06 | Test colour display | Follow the display manufacturer's examples and library for the exact display model. Display a simple face and two eyes before installing it in the shell. | P05 | 2–4 hours | Not started
P07 | Test one motor channel | Keep wheels off the ground. Wire one motor through its driver, use a low speed, test forward/reverse, then stop. Never connect a motor directly to Pico GPIO. | P02, P05 | 2–3 hours | Not started
P08 | Test all four motors | Repeat for all channels. Check motor current, driver temperature, direction and whether the Pico resets when motors start. Use suitable motor power and common ground as required by the circuit. | P07 | 2–4 hours | Not started
P09 | Build base chassis | Print or make a simple base plate first. Fit four motor mounts underneath, with wheel clearance. Add screw holes and removable electronics/battery mounts. | P01, P08 | 4–8 hours | Not started
P10 | Install battery and wiring | Secure battery so it cannot move. Keep motor wiring away from wheels. Use a suitable regulated supply for Pico/display and a safe, correctly rated battery arrangement. | P08, P09 | 2–4 hours | Not started
P11 | Add obstacle sensor | Connect the distance sensor using its datasheet and a compatible logic voltage. Test readings while stationary before adding automatic reactions. | P05 | 2–3 hours | Not started
P12 | Add camera-mount servo | Power the servo from an appropriate supply, not directly from a Pico GPIO. Connect signal and ground correctly; test limited angles before fitting the camera mount. | P05, P10 | 2–3 hours | Not started
P13 | Build phone-app control | Use Pico W Wi-Fi for a simple local web page with Forward, Reverse, Left, Right and Stop. Add a timeout so movement stops if commands stop arriving. Use only on a trusted local network. | P08 | 4–8 hours | Not started
P14 | Combine software modules | Integrate motor, display, sensor, servo and remote-control modules. Keep code separated into files; test each module individually before integration. | P06, P08, P11, P12, P13 | 4–8 hours | Not started
P15 | Safety and driving tests | First test with wheels raised. Then test slowly in an open area. Confirm Stop works, obstacle response is predictable, wiring is secure and motors/drivers do not overheat. | P14 | 2–4 hours | Not started
P16 | Final shell and appearance | After the prototype works, print the rounded-square shell with display opening, ventilation, removable cover, four wheel cut-outs and camera-mount fixing points. | P15 | 4–10 hours | Not started
P17 | Optional track conversion | Only after wheeled version is reliable: design matching drive sprockets/idlers, belt tensioning and brackets. Track kits must match the chassis and motor arrangement. | P16 | Variable | Not started
P18 | Optional live video | Pico W is not suited to full conventional camera streaming by itself. Add a separate camera-capable computer/module and camera if live video is required. | P15 | Variable | Not started

## Parts & Costs
PARTS SUPPLY & COSTS
AUD estimates for planning only. Confirm exact model, electrical compatibility, shipping and stock before ordering.
ID | Part / quantity | What to check | Low estimate (AUD) | High estimate (AUD) | Budget used (AUD) | Supplier / search link | Essential? | Ordered? | Received?
E01 | Raspberry Pi Pico W × 1 | Wi-Fi model; headers may need soldering depending on variant. | 9.5 | 18 |  | https://core-electronics.com.au/raspberry-pi-pico-w-wireless-wifi.html | Yes | No | No
E02 | Pico Display Pack 2.0 × 1 | Confirm exact model and library; approx 56 × 35 mm board footprint. | 30 | 45 |  | https://core-electronics.com.au/pico-display-pack-2-0.html | Yes | No | No
E03 | Dual-channel motor driver boards × 2 (provisional) | Choose only after confirming motor voltage and stall current; one board may drive two motors if rated appropriately. | 25 | 55 |  | https://www.robotgear.com.au/Product.aspx/Details/5513-SparkFun-Motor-Driver-Dual-TB6612FNG-with-Headers | Yes | No | No
E04 | Geared DC motors × 4 | Matching voltage, shaft, speed/torque and stall current. Avoid choosing by appearance alone. | 30 | 60 |  | https://www.amazon.com.au/s?k=N20+6V+geared+motor | Yes | No | No
E05 | Wheels and hubs × 4 | Hub must fit exact motor shaft; confirm diameter and body clearance. | 10 | 25 |  | https://www.amazon.com.au/s?k=small+robot+wheels+N20 | Yes | No | No
E06 | Battery pack/holder and power wiring × 1 set | Voltage and current must suit motors and driver; separate regulated supply for logic may be needed. | 20 | 40 |  | https://www.jaycar.com.au/search?text=battery+holder | Yes | No | No
E07 | Distance sensor × 1 | VL53L0X or compatible module; check logic voltage and library. | 10 | 25 |  | https://www.mlab.com.au/products/gravity-vl53l0x-tof-distance-sensor-30-2000mm | Optional but recommended | No | No
E08 | Micro servo × 1 | For camera mount; use a suitable servo supply and shared ground as required. | 5 | 15 |  | https://www.jaycar.com.au/search?text=servo | Optional | No | No
E09 | USB data cable × 1 | Check the connector on the chosen Pico board; cable must support data, not charge-only. | 5 | 12 |  | https://www.jaycar.com.au/search?text=USB+data+cable | Yes | No | No
E10 | Jumper wires / prototyping board / connectors | Include suitable wire gauge for motor current and insulated connectors. | 10 | 25 |  | https://core-electronics.com.au/search.php?search_query=Raspberry+Pi+Pico+protoboard | Yes | No | No
E11 | Screws, nuts, spacers, switch | Allow for mounting boards, battery and shell. | 8 | 20 |  | https://www.amazon.com.au/s?k=M3+screws+nuts+spacers+kit | Yes | No | No
M01 | 3D printing / filament / base plate | Prototype base first; final shell after measuring parts. | 20 | 50 |  | https://www.printables.com/search/models?q=robot%20chassis | Yes | No | No
O01 | Track kit / sprockets / idlers | Optional future upgrade; must match chassis and motors. | 20 | 60 |  | https://www.amazon.com.au/s?k=small+robot+tracked+chassis+kit | Optional | No | No
O02 | Camera + separate camera-capable board | Optional live video; Pico W alone is not recommended for normal camera streaming. | 35 | 100 |  | https://core-electronics.com.au/search.php?search_query=Raspberry+Pi+camera | Optional | No | No
O03 | Tools / solder / heat-shrink / spare parts | Depends on tools already owned. | 0 | 40 |  | https://www.jaycar.com.au/ | Maybe | No | No
Essential build estimate (excluding optional items)
All items including optional upgrades

## Software Plan
SOFTWARE DEVELOPMENT PLAN
Build each feature independently in MicroPython, then integrate. Pin numbers depend on the final display and driver.
Order | Module / file | Goal | Development instructions | Test / acceptance criteria | Useful link | Status
1 | setup_notes.md | Record exact hardware and pins | Write down Pico model, display model, driver model, motor voltage/current, power rails, I2C/SPI pins and library versions. Do not guess pin mappings. | A wiring map exists before full assembly. | https://www.raspberrypi.com/documentation/microcontrollers/micropython.html | Not started
2 | main.py | Startup and coordination | Initialise modules; show startup face; keep main loop responsive; stop motors on errors or lost control commands. | Robot starts predictably and defaults to stopped. | https://thonny.org/ | Not started
3 | face.py | Animated eyes | Use the exact display library. Start with static eyes, then blinking and a few expressions. Keep display updates separate from motor-control timing. | Face updates without freezing motor or safety logic. | https://core-electronics.com.au/pico-display-pack-2-0.html | Not started
4 | motors.py | Drive and turn | Implement stop(), forward(speed), reverse(speed), left(speed), right(speed). Limit speed range and test wheels off the ground. Use motor driver; never drive motors from GPIO directly. | Each command does what it says; stop command works immediately. | https://www.raspberrypi.com/documentation/microcontrollers/pico-series.html | Not started
5 | sensor.py | Obstacle distance | Read sensor using its library and datasheet. Filter implausible readings and define a cautious stop distance. Test stationary before autonomous reactions. | Valid distance readings; robot stops or refuses forward movement near an obstacle. | https://www.mlab.com.au/products/gravity-vl53l0x-tof-distance-sensor-30-2000mm | Not started
6 | camera_mount.py | Servo movement | Use PWM to command a limited angle range. Power servo from suitable supply, not a GPIO pin. Start with camera absent to avoid overloading mount. | Mount moves smoothly without buzzing or hitting mechanical stops. | https://www.raspberrypi.com/documentation/microcontrollers/micropython.html | Not started
7 | remote.py | Phone control over Wi-Fi | Host a simple local control page or accept authenticated local commands. Add a command timeout/dead-man stop; do not expose the robot directly to the public internet. | Phone can command movement on local network; loss of commands stops the robot. | https://www.raspberrypi.com/documentation/microcontrollers/micropython.html | Not started
8 | integration | Combine features | Test each module alone, then combine one at a time. Avoid long blocking delays; use timing that keeps the stop/safety loop responsive. | Display, motors, sensor, servo and app control operate together. | https://projects.raspberrypi.org/en/projects/introduction-to-the-pico | Not started
9 | optional camera subsystem | Live video | Use a separate camera-capable computer/module if streaming video is required. Keep video processing separate from the Pico's motor control. | Video works without interrupting motor stop/safety behavior. | https://core-electronics.com.au/search.php?search_query=Raspberry+Pi+camera | Not started

## Wiring & Test Log
WIRING NOTES & TEST LOG
Fill in actual pins and results only after checking the specific component datasheets.
Subsystem | Signal / connection | Pico pin / board terminal | Power source / voltage | Test procedure | Expected result | Actual result / notes | Pass?
Display | SPI/I2C/control pins | Fill from exact display documentation | As specified by display board | Run display demo before attaching motors | Face renders without flicker or reset |  | Not tested
Motor driver A | Control inputs and motor outputs | Fill from driver datasheet and code | Motor supply within driver/motor ratings | Wheels raised; low speed; test forward/reverse/stop | Motor responds correctly; no overheating |  | Not tested
Motor driver B | Control inputs and motor outputs | Fill from driver datasheet and code | Motor supply within driver/motor ratings | Test each motor individually | All motors respond as expected |  | Not tested
Distance sensor | SDA/SCL or required interface | Fill from sensor documentation | Check logic voltage compatibility | Read several distances with robot stationary | Stable plausible readings |  | Not tested
Servo | PWM signal and ground | Fill from chosen pin plan | Suitable servo supply; not powered from GPIO | Move through limited angles with mount unloaded | Smooth movement; no excessive buzzing |  | Not tested
Pico power | VSYS/USB/power input as designed | Use official board docs | Regulated supply within board limits | Power-cycle and monitor stability | Pico starts reliably |  | Not tested
Phone app | Wi-Fi connection and commands | Pico W wireless | Local trusted Wi-Fi network | Test each button and disconnect phone | Stop timeout halts motion |  | Not tested