## Review v2
PLAN REVIEW AND ADAPTATIONS (v2)
Review of the original plan, adding a walking body, a hand and a voice. Orange rows on other sheets are new in v2.
How to use | Try designs in sandbox/index.html first, check them with python sim/bench.py, then follow the stage tasks P19-P32 on Project Plan.
Type | Topic | Finding | Change in v2
Keep | Staged, test-each-module-first approach | This is the right way to build robots. Every later stage in v2 follows the same rule: prove it in the sandbox, then on the bench, then on the floor. | No change
Keep | Safety rules (wheels raised, dead-man timeout, no motors on GPIO, trusted Wi-Fi only) | These are correct and they matter more once the robot has legs and an arm. They are copied into every new stage. | No change
Keep | N20 1:298 motors with TB6612 drivers | Physics bench: the 385 g Hatchling reaches 0.18 m/s and climbs a 35 degree ramp. Plenty of torque. The TB6612 (1.2 A per channel continuous) suits N20 stall currents. | No change
Adapt | Ground clearance limits steps to about 10 mm | Physics bench: wheels mount 10 mm and the tracked version 15 mm (with 44 mm sprockets). Neither manages the 20 mm kerb goal. The belly hits the edge. | Raise the floor of the shell by 5 to 8 mm, or use bigger wheels. Test again in sim/bench.py.
Adapt | Choose N20 motors with hall encoders | Encoders count wheel turns. The robot can then drive exact distances, which the digital twin and autonomous tasks need. They cost a few dollars more per motor. | Change E04 to encoder N20s (6 extra Pico pins)
Adapt | Plan the shell around two brains from day one | Pico W is right for stage 1 (motors, face, sensor). Video, walking, speech and the hand all need a Linux board. A Pi Zero 2 W is 65 x 30 mm. | Leave a 70 x 35 mm bay and a 5 V 3 A supply rail in the stage 1 shell
Adapt | Power: move to a 2S (7.4 V) pack with a BMS before stage 3 | Bus servos (STS3215) need about 7.4 V. 4x AA NiMH at 4.8 V is fine for stage 1 only. Add a fuse, a switch and a 5 V buck converter for the Pi. | New part U07 and U08; supervised charging in a LiPo bag
Adapt | Walking: adopt the Open Duck Mini legs and policy, don't design new legs | Open Duck Mini is open source (Apache-2.0), about 42 cm tall, uses a Pi Zero 2 W and already has a trained walking policy. Ten STS3215 servos will not fit in a 120 mm body: they need about a 170 mm body. | Stage 3 = build the duck's legs and put the OreVis shell, face and camera on top. Keep added mass under about 150 g. See sim/OPEN_DUCK.md
Adapt | Use one servo family for legs, arm and hand | Feetech serial-bus servos (STS3215, SCS0009) share one 3-wire bus and one driver board, and report their angle. Open Duck, the LeRobot SO-101 arm and Pollen's Amazing Hand all use them. | Standardise on Feetech bus servos for stages 3 to 5
Adapt | Hand: start with a light 3-finger hand, not the full humanoid hand | Pollen's Amazing Hand is about 400 g. The physics bench shows the 1.36 kg walker tips 44 degrees holding it out. A 45 g 3-finger tendon hand holds a 20 g block at 64% of shoulder stall with no tipping. | Stage 4 = 3-finger hand. Try the Amazing Hand later on a bench-mounted arm
Adapt | A walking robot must squat to pick things off the floor | Sandbox: with a 17 cm arm mounted 26 cm up, the Helper only reaches the floor by squatting about 63 degrees at the knee. The bench shows STS3215 knees peak at 36% of stall in that squat, which is fine. | Add a squat-and-reach behaviour (sandbox already does it)
Adapt | Software: write behaviours once, run them in the twin and on the robot | Give motors, servos and sensors the same small interface in the sandbox, MuJoCo and the robot. Tested behaviour code can then move to hardware unchanged. | New software row 10: hal.py
Fix | P04 does not need to wait for parts (P03) | The computer, Thonny and the sandbox can all be set up while parts ship. | P04 dependency changed to None
Fix | P18 live video now has a home | Stage 2 adds the Pi Zero 2 W, which streams the camera. The Pico keeps doing motors and the face. | P18 linked to stage 2 tasks

## Project Plan
ROBOT BUILD PROJECT PLAN
Rounded-square robot • Raspberry Pi Pico W • colour face • four wheels underneath • optional tracks later
Project goal | Build a small rounded-square robot with a colour display for animated eyes, four powered wheels, a servo-operated camera mount, an obstacle sensor and phone-app control over Wi-Fi. Start with a wheeled prototype; add tracks and live camera video only after the basics work.
Planning budget (AUD) | See Parts & Costs tab; estimates only, verify current pricing and compatibility before buying.
ID | Stage / task | Instructions / deliverable | Dependency | Estimate | Status
P01 | Confirm design dimensions | Measure the display, Pico board, motors, wheel diameter, battery and camera mount. Draw the internal layout and wheel openings. Do not finalise the shell before measuring real parts. | None | 2–4 hours | Not started
P02 | Confirm compatible electronics | Choose motors and check their stall current against the motor-driver ratings. Confirm display interface/library, servo supply, battery voltage and regulated logic supply. | P01 | 2–3 hours | Not started
P03 | Order essential parts | Use the Parts & Costs tab. Buy only after checking seller stock, delivery, connectors and voltage/current specs. | P02 | 1 hour | Not started
P04 | Set up development computer | Install Thonny. Download the correct MicroPython UF2 for Pico W. Connect using a USB data cable; hold BOOTSEL while plugging in, then copy the UF2 file if needed. | None (v2: start while parts ship) | 1–2 hours | Not started
P05 | First Pico test | In Thonny, select MicroPython for Pico. Run print('Hello robot'). Save a simple program to the Pico as main.py and confirm it runs after power cycling. | P04 | 1–2 hours | Not started
P06 | Test colour display | Follow the display manufacturer's examples and library for the exact display model. Display a simple face and two eyes before installing it in the shell. | P05 | 2–4 hours | Not started
P07 | Test one motor channel | Keep wheels off the ground. Wire one motor through its driver, use a low speed, test forward/reverse, then stop. Never connect a motor directly to Pico GPIO. | P02, P05 | 2–3 hours | Not started
P08 | Test all four motors | Repeat for all channels. Check motor current, driver temperature, direction and whether the Pico resets when motors start. Use suitable motor power and common ground as required by the circuit. | P07 | 2–4 hours | Not started
P09 | Build base chassis | Print or make a simple base plate first. Fit four motor mounts underneath, with wheel clearance. Add screw holes and removable electronics/battery mounts. | P01, P08 | 4–8 hours | Not started
P10 | Install battery and wiring | Secure battery so it cannot move. Keep motor wiring away from wheels. Use a suitable regulated supply for Pico/display and a safe, correctly rated battery arrangement. | P08, P09 | 2–4 hours | Not started
P11 | Add obstacle sensor | Connect the distance sensor using its datasheet and a compatible logic voltage. Test readings while stationary before adding automatic reactions. | P05 | 2–3 hours | Not started
P12 | Add camera-mount servo | Power the servo from an appropriate supply, not directly from a Pico GPIO. Connect signal and ground correctly; test limited angles before fitting the camera mount. | P05, P10 | 2–3 hours | Not started
P13 | Build phone-app control | Use Pico W Wi-Fi for a simple local web page with Forward, Reverse, Left, Right and Stop. Add a timeout so movement stops if commands stop arriving. Use only on a trusted local network. | P08 | 4–8 hours | Not started
P14 | Combine software modules | Integrate motor, display, sensor, servo and remote-control modules. Keep code separated into files; test each module individually before integration. | P06, P08, P11, P12, P13 | 4–8 hours | Not started
P15 | Safety and driving tests | First test with wheels raised. Then test slowly in an open area. Confirm Stop works, obstacle response is predictable, wiring is secure and motors/drivers do not overheat. | P14 | 2–4 hours | Not started
P16 | Final shell and appearance | After the prototype works, print the rounded-square shell with display opening, ventilation, removable cover, four wheel cut-outs and camera-mount fixing points. | P15 | 4–10 hours | Not started
P17 | Optional track conversion | Only after wheeled version is reliable: design matching drive sprockets/idlers, belt tensioning and brackets. Track kits must match the chassis and motor arrangement. | P16 | Variable | Not started
P18 | Optional live video | Pico W is not suited to full conventional camera streaming by itself. Add a separate camera-capable computer/module and camera if live video is required. v2: done in stage 2 with a Pi Zero 2 W (P19-P20). | P15 | Variable | Not started
v2: evolution stages (see Evolution Roadmap)
P00 | Try the design in the sandbox | Open sandbox/index.html. Drive the Hatchling, finish missions 1-2, then try other motors, wheels and batteries. Save the designs you like and compare them. | None | 1-2 hours | Not started
P19 | Stage 2: add encoders and a Pi Zero 2 W | Swap to encoder N20s. Mount the Pi Zero 2 W in the reserved bay. Link it to the Pico over UART (TX/RX/GND). The Pico keeps the motors and the dead-man stop. | P15 | 4-6 hours | Not started
P20 | Stage 2: live camera | Fit the Pi camera to the spiral mount. Stream video on the local network only. Check the stream does not slow the Pico's stop command. | P19 | 3-5 hours | Not started
P21 | Stage 2: tracks | Fit 44 mm sprockets and track panels (P17). Run sim/bench.py on your measured design first; raise ground clearance until the bench mounts 20 mm. | P17, P19 | Variable | Not started
P22 | Stage 3: run Open Duck in simulation | Install uv and Open_Duck_Playground. Run mujoco_infer.py with a trained policy and watch the duck walk. No hardware needed. | P00 | 2-3 hours | Not started
P23 | Stage 3: build the duck legs | Print and assemble the Open Duck Mini v2 legs. Set each STS3215 servo ID and test it alone with the bus board before assembly. | P22 | 15-25 hours | Not started
P24 | Stage 3: power and IMU | 2S pack with BMS, fuse, switch and 5 V 3 A buck for the Pi. Fit the BNO055 IMU near the centre of the body and test it. | P23 | 3-5 hours | Not started
P25 | Stage 3: first steps | Follow the Open_Duck_Mini_Runtime setup, find joint offsets, then run the walk policy on a soft floor with a hand ready to catch. | P24 | 4-8 hours | Not started
P26 | Stage 3: OreVis head on the duck | Mount the shell, face display and camera on top. Keep added mass under about 150 g and centred; re-check walking. | P25 | 4-8 hours | Not started
P27 | Stage 4: arm and 3-finger hand | Print the 4-servo arm and tendon hand. Run sim/bench.py with your real masses before printing. Test the arm clamped to the bench first. | P26 | 10-15 hours | Not started
P28 | Stage 4: squat-and-reach | Program the squat, reach, grip and lift sequence (the sandbox shows the steps). Test it standing still before trying it while walking. | P27 | 6-10 hours | Not started
P29 | Stage 4: retrain walking with the arm | Copy open_duck_mini_v2 in the Playground, add the arm and hand mass, train, and test in MuJoCo before the robot. | P27 | 1-2 days (GPU) | Not started
P30 | Stage 5: Pi 5, microphone and speaker | Swap the brain to a Pi 5. Add an I2S amp and speaker and a USB microphone. Test speech in and out with the robot standing still. | P28 | 4-6 hours | Not started
P31 | Stage 5: voice commands | Map spoken requests to the same commands the sandbox uses (pick red, place blue, go to pad). Always obey 'stop' first. | P30 | 6-10 hours | Not started
P32 | Stage 5: first autonomous task | Tidy-up: find coloured blocks with the camera, carry each to its bin. Run it in the sandbox until it never fails, then on the real floor. | P31 | Variable | Not started

## Evolution Roadmap
EVOLUTION ROADMAP
Each stage keeps the last one working. Mass and AUD come from the sandbox design model (planning estimates).
Stage | Name | What it adds | Brain | Moves on | New abilities | Gate test before moving on | Mass | Parts AUD
1 | Hatchling | The original plan: rounded-square body, four wheels, Pico W, colour face, VL53L0X, camera tilt servo, phone control. | Pico W | 4x N20 wheels | Drive, face, stop for obstacles | Sandbox missions 1-2; bench: 15 degree ramp | 385 g | $176-377
2 | Explorer | Track panels on 44 mm sprockets, Pi Zero 2 W + camera for live video. Encoders for exact moves. | Pico W + Pi Zero 2 W | Tracks | Live video, kerbs, mapping the room | Bench: step >= 20 mm (needs more clearance) | 432 g | $256-524
3 | Duckling | Grows legs: Open Duck Mini v2 legs (10x STS3215), BNO055 IMU, 2S battery. OreVis shell becomes the head and body. | Pi Zero 2 W | Two legs | Walks with the Open Duck policy | Bench: stand + squat; Open Duck MuJoCo inference walks | about 1.1 kg | $503-875
4 | Helper | Adds a 4-servo STS3215 arm and a 3-finger tendon hand on the right shoulder. | Pi Zero 2 W | Two legs | Squat, pick a block, carry it to a bin | Sandbox: Tidy-up mission; bench: arm hold, no tipping | about 1.4 kg | $621-1075
5 | Companion | Pi 5 brain, microphone and speaker. Talks, listens and plans simple jobs. | Pi 5 (4 GB) | Two legs | Talk, follow spoken requests, do tasks alone | Sandbox: talk and tidy missions | about 1.4 kg | $711-1200

## Parts & Costs
PARTS SUPPLY & COSTS
AUD estimates for planning only. Confirm exact model, electrical compatibility, shipping and stock before ordering.
ID | Part / quantity | What to check | Low estimate (AUD) | High estimate (AUD) | Budget used (AUD) | Supplier / search link | Essential? | Ordered? | Received?
E01 | Raspberry Pi Pico W × 1 | Wi-Fi model; headers may need soldering depending on variant. | 9.5 | 18 |  | https://core-electronics.com.au/raspberry-pi-pico-w-wireless-wifi.html | Yes | No | No
E02 | Pico Display Pack 2.0 × 1 | Confirm exact model and library; approx 56 × 35 mm board footprint. | 30 | 45 |  | https://core-electronics.com.au/pico-display-pack-2-0.html | Yes | No | No
E03 | Dual-channel motor driver boards × 2 (provisional) | Choose only after confirming motor voltage and stall current; one board may drive two motors if rated appropriately. | 25 | 55 |  | https://www.robotgear.com.au/Product.aspx/Details/5513-SparkFun-Motor-Driver-Dual-TB6612FNG-with-Headers | Yes | No | No
E04 | Geared DC motors × 4 | Matching voltage, shaft, speed/torque and stall current. Avoid choosing by appearance alone. | 30 | 60 |  | https://www.amazon.com.au/s?k=N20+6V+geared+motor | Yes | No | No
E05 | Wheels and hubs × 4 | Hub must fit exact motor shaft; confirm diameter and body clearance. | 10 | 25 |  | https://www.amazon.com.au/s?k=small+robot+wheels+N20 | Yes | No | No
E06 | Battery pack/holder and power wiring × 1 set | Voltage and current must suit motors and driver; separate regulated supply for logic may be needed. | 20 | 40 |  | https://www.jaycar.com.au/search?text=battery+holder | Yes | No | No
E07 | Distance sensor × 1 | VL53L0X or compatible module; check logic voltage and library. | 10 | 25 |  | https://www.mlab.com.au/products/gravity-vl53l0x-tof-distance-sensor-30-2000mm | Optional but recommended | No | No
E08 | Micro servo × 1 | For camera mount; use a suitable servo supply and shared ground as required. | 5 | 15 |  | https://www.jaycar.com.au/search?text=servo | Optional | No | No
E09 | USB data cable × 1 | Check the connector on the chosen Pico board; cable must support data, not charge-only. | 5 | 12 |  | https://www.jaycar.com.au/search?text=USB+data+cable | Yes | No | No
E10 | Jumper wires / prototyping board / connectors | Include suitable wire gauge for motor current and insulated connectors. | 10 | 25 |  | https://core-electronics.com.au/search.php?search_query=Raspberry+Pi+Pico+protoboard | Yes | No | No
E11 | Screws, nuts, spacers, switch | Allow for mounting boards, battery and shell. | 8 | 20 |  | https://www.amazon.com.au/s?k=M3+screws+nuts+spacers+kit | Yes | No | No
M01 | 3D printing / filament / base plate | Prototype base first; final shell after measuring parts. | 20 | 50 |  | https://www.printables.com/search/models?q=robot%20chassis | Yes | No | No
O01 | Track kit / sprockets / idlers | Optional future upgrade; must match chassis and motors. | 20 | 60 |  | https://www.amazon.com.au/s?k=small+robot+tracked+chassis+kit | Optional | No | No
O02 | Camera + separate camera-capable board | Optional live video; Pico W alone is not recommended for normal camera streaming. | 35 | 100 |  | https://core-electronics.com.au/search.php?search_query=Raspberry+Pi+camera | Optional | No | No
O03 | Tools / solder / heat-shrink / spare parts | Depends on tools already owned. | 0 | 40 |  | https://www.jaycar.com.au/ | Maybe | No | No
Essential build estimate (excluding optional items)
All items including optional upgrades
v2: parts for later stages (buy each stage only after the one before works)
ID | Part / quantity | What to check | Low estimate (AUD) | High estimate (AUD) | Budget used (AUD) | Supplier / search link | Stage | Ordered? | Received?
U01 | Raspberry Pi Zero 2 W x 1 | Stage 2 brain for video, walking policy and bus servos. 65 x 30 mm. | 25 | 35 |  | https://core-electronics.com.au/raspberry-pi-zero-2-w-wireless.html | Stage 2 | No | No
U02 | N20 6V 1:298 motors with hall encoders x 4 | Replaces E04 if bought before stage 1. Check shaft and connector. | 40 | 80 |  | https://www.amazon.com.au/s?k=N20+encoder+gear+motor+6V | Stage 1-2 | No | No
U03 | Track panels and 44 mm sprockets | Replaces O01. Print or buy; must match motor shaft. | 20 | 60 |  | https://www.printables.com/search/models?q=robot%20track | Stage 2 | No | No
U04 | Feetech STS3215 servos x 10 (legs) | Open Duck Mini v2 legs. Order a spare or two. | 250 | 400 |  | https://github.com/apirrone/Open_Duck_Mini | Stage 3 | No | No
U05 | Feetech bus servo driver board | USB to serial bus board for the Pi. | 15 | 30 |  | https://www.feetechrc.com/ | Stage 3 | No | No
U06 | BNO055 IMU | Absolute orientation sensor used by Open Duck. | 35 | 55 |  | https://core-electronics.com.au/search.php?search_query=BNO055 | Stage 3 | No | No
U07 | 2S 7.4 V battery with BMS + charger | 18650 2S pack or 2S LiPo 2200 mAh. Charge supervised, in a LiPo bag. | 45 | 90 |  | https://www.jaycar.com.au/search?text=7.4V+battery | Stage 3 | No | No
U08 | 5 V 3 A buck converter, fuse, switch | Clean supply for the Pi from the 2S pack. | 15 | 30 |  | https://core-electronics.com.au/search.php?search_query=buck+converter+5V+3A | Stage 3 | No | No
U09 | Feetech STS3215 servos x 4 (arm) | Yaw, shoulder, elbow, wrist. | 100 | 160 |  | https://www.feetechrc.com/ | Stage 4 | No | No
U10 | 3-finger tendon hand (2 micro servos + printed parts) | About 45 g. Fishing line tendons, elastic return. | 15 | 30 |  | https://www.printables.com/search/models?q=robot%20hand%20tendon | Stage 4 | No | No
U11 | Raspberry Pi 5 (4 GB) + cooler | Stage 5 brain for speech and vision. | 95 | 125 |  | https://core-electronics.com.au/raspberry-pi-5-model-b-4gb.html | Stage 5 | No | No
U12 | I2S amp (MAX98357), speaker, USB microphone | Voice in and out. | 20 | 40 |  | https://core-electronics.com.au/search.php?search_query=MAX98357 | Stage 5 | No | No
O04 | Pollen Amazing Hand kit (optional) | 8 servos, about 400 g. Too heavy for the walker; use on a bench arm. | 300 | 380 |  | https://huggingface.co/blog/pollen-robotics/amazing-hand | Optional | No | No
Later stages, excluding optional items

## Software Plan
SOFTWARE DEVELOPMENT PLAN
Build each feature independently in MicroPython, then integrate. Pin numbers depend on the final display and driver.
Order | Module / file | Goal | Development instructions | Test / acceptance criteria | Useful link | Status
1 | setup_notes.md | Record exact hardware and pins | Write down Pico model, display model, driver model, motor voltage/current, power rails, I2C/SPI pins and library versions. Do not guess pin mappings. | A wiring map exists before full assembly. | https://www.raspberrypi.com/documentation/microcontrollers/micropython.html | Not started
2 | main.py | Startup and coordination | Initialise modules; show startup face; keep main loop responsive; stop motors on errors or lost control commands. | Robot starts predictably and defaults to stopped. | https://thonny.org/ | Not started
3 | face.py | Animated eyes | Use the exact display library. Start with static eyes, then blinking and a few expressions. Keep display updates separate from motor-control timing. | Face updates without freezing motor or safety logic. | https://core-electronics.com.au/pico-display-pack-2-0.html | Not started
4 | motors.py | Drive and turn | Implement stop(), forward(speed), reverse(speed), left(speed), right(speed). Limit speed range and test wheels off the ground. Use motor driver; never drive motors from GPIO directly. | Each command does what it says; stop command works immediately. | https://www.raspberrypi.com/documentation/microcontrollers/pico-series.html | Not started
5 | sensor.py | Obstacle distance | Read sensor using its library and datasheet. Filter implausible readings and define a cautious stop distance. Test stationary before autonomous reactions. | Valid distance readings; robot stops or refuses forward movement near an obstacle. | https://www.mlab.com.au/products/gravity-vl53l0x-tof-distance-sensor-30-2000mm | Not started
6 | camera_mount.py | Servo movement | Use PWM to command a limited angle range. Power servo from suitable supply, not a GPIO pin. Start with camera absent to avoid overloading mount. | Mount moves smoothly without buzzing or hitting mechanical stops. | https://www.raspberrypi.com/documentation/microcontrollers/micropython.html | Not started
7 | remote.py | Phone control over Wi-Fi | Host a simple local control page or accept authenticated local commands. Add a command timeout/dead-man stop; do not expose the robot directly to the public internet. | Phone can command movement on local network; loss of commands stops the robot. | https://www.raspberrypi.com/documentation/microcontrollers/micropython.html | Not started
8 | integration | Combine features | Test each module alone, then combine one at a time. Avoid long blocking delays; use timing that keeps the stop/safety loop responsive. | Display, motors, sensor, servo and app control operate together. | https://projects.raspberrypi.org/en/projects/introduction-to-the-pico | Not started
9 | optional camera subsystem | Live video | Use a separate camera-capable computer/module if streaming video is required. Keep video processing separate from the Pico's motor control. | Video works without interrupting motor stop/safety behavior. | https://core-electronics.com.au/search.php?search_query=Raspberry+Pi+camera | Not started
10 | hal.py | Same code in twin and robot | Small classes Motor, Servo, Distance, Imu with the same methods in the sandbox, in MuJoCo and on the robot. Behaviours only talk to these. | A behaviour runs unchanged in sim and on the robot. | sandbox/model.js, sim/robot_xml.py | Not started
11 | link.py (Pi <-> Pico) | Stage 2 two-brain link | JSON lines over UART: the Pi sends drive and face commands, the Pico replies with sensor readings. The Pico still stops on its own if messages stop. | Unplugging the Pi stops the robot within 0.5 s. | https://docs.micropython.org/en/latest/library/machine.UART.html | Not started
12 | walk (Open Duck runtime) | Walking | Use Open_Duck_Mini_Runtime unchanged first. Wrap it so hal.py can ask for 'walk at speed v, turn w'. | Robot walks forward, turns and stops on command. | https://github.com/apirrone/Open_Duck_Mini_Runtime | Not started
13 | arm.py | Squat, reach, grip, lift | Two-link IK as in the sandbox; plan squat depth from target height. Check servo load readings and stop if over 80%. | Picks a 30 mm block from the floor 9 times out of 10. | sandbox/index.html (planReach, solveArm) | Not started
14 | voice.py | Listen and talk | Wake word, then speech-to-text, then the same command parser as the sandbox. Say 'stop' always wins. | Understands 'pick up the red block' and 'stop'. | https://github.com/rhasspy/piper | Not started
15 | tasks.py | Do jobs alone | Tidy-up: find blocks by colour with the camera, then pick and place each one. Develop it in the sandbox first. | Finishes the sandbox Tidy-up mission, then the real one. | sandbox mission 8 | Not started

## Wiring & Test Log
WIRING NOTES & TEST LOG
Fill in actual pins and results only after checking the specific component datasheets.
Subsystem | Signal / connection | Pico pin / board terminal | Power source / voltage | Test procedure | Expected result | Actual result / notes | Pass?
Display | SPI/I2C/control pins | Fill from exact display documentation | As specified by display board | Run display demo before attaching motors | Face renders without flicker or reset |  | Not tested
Motor driver A | Control inputs and motor outputs | Fill from driver datasheet and code | Motor supply within driver/motor ratings | Wheels raised; low speed; test forward/reverse/stop | Motor responds correctly; no overheating |  | Not tested
Motor driver B | Control inputs and motor outputs | Fill from driver datasheet and code | Motor supply within driver/motor ratings | Test each motor individually | All motors respond as expected |  | Not tested
Distance sensor | SDA/SCL or required interface | Fill from sensor documentation | Check logic voltage compatibility | Read several distances with robot stationary | Stable plausible readings |  | Not tested
Servo | PWM signal and ground | Fill from chosen pin plan | Suitable servo supply; not powered from GPIO | Move through limited angles with mount unloaded | Smooth movement; no excessive buzzing |  | Not tested
Pico power | VSYS/USB/power input as designed | Use official board docs | Regulated supply within board limits | Power-cycle and monitor stability | Pico starts reliably |  | Not tested
Phone app | Wi-Fi connection and commands | Pico W wireless | Local trusted Wi-Fi network | Test each button and disconnect phone | Stop timeout halts motion |  | Not tested
Pi Zero 2 W link | UART TX/RX/GND to Pico | Pico UART0 pins, Pi GPIO14/15 | 5 V buck for Pi, common ground | Send a test message each way | Messages arrive; stop works when unplugged |  | Not tested
Bus servos | Data line via bus driver board | Pi USB | 2S 7.4 V through fuse | One servo at a time: set ID, move 10 degrees | Correct ID, position read back |  | Not tested
IMU (BNO055) | I2C SDA/SCL | Pi I2C | 3.3 V | Tilt the robot by hand | Angles follow the tilt |  | Not tested
2S battery + BMS | Main power | Switch and fuse | 7.4 V nominal, 8.4 V full | Measure voltage, then power one servo | No resets or brown-outs |  | Not tested
Arm and hand | Bus servos 11-14 + hand servos | Bus driver board | 7.4 V servos, 5 V micro servos | Arm clamped on the bench, hold horizontal with block | Load under 70% of stall, no buzzing |  | Not tested

## Sandbox Results
DIGITAL TWIN RESULTS
From python sim/bench.py sim/designs/*.json (MuJoCo physics). Re-run after every design change.
Design | Moves on | Mass (g) | Top speed (m/s) | Steepest ramp (deg) | Tallest step (mm) | Stands / squats | Knee peak (% stall) | Arm out: shoulder load | Arm out: body tilt (deg) | Verdict
Hatchling | wheels | 385 | 0.176 | 35 | 10 |  |  |  |  | steps only 10 mm
Explorer | tracks | 432 | 0.225 | 25 | 15 |  |  |  |  | steps only 15 mm
Duckling | legs | 1076 |  |  |  | yes / yes | 32 |  |  | OK
Helper | legs | 1361 |  |  |  | yes / yes | 36 | 64% | 0.5 | OK
Companion | legs | 1429 |  |  |  | yes / yes | 40 | 64% | 0.4 | OK
Hatchling + micro-servo arm | wheels | 480 | 0.176 | 35 | 10 |  |  | 93% | 0 | steps only 10 mm; shoulder near stall
Helper + Amazing Hand | legs | 1716 |  |  |  | yes / yes | 39 | 100% | 43.6 | tips over with arm out; shoulder near stall
Mini duck on SG90 servos | legs | 473 |  |  |  | yes / yes | 100 |  |  | knees at stall